## ocs template
Engineer's Representative: ASTAD Project Management |  |  |  |  | Main Contractor: |  | ARCON | Employer: HMC
Observations & Comments Sheet (OCS) | [8 empty] | CLASSIFICATION:
Design Stage
Construction Stage
Project Scope: |  | Contruction for Upgrating Fire Life Safety and CCTV Systems
Contract No.: |  | TCS/22/2018 |  |  |  |  | ASSESSMENT CODE:
Project Title: |  | Construction & Upgrading Fire Life Safety and CCTV for the Heart Hospital & NCCCR |  |  |  |  | A = Approved/No Comments.
Project Code/No.: |  | MRC.HH.01 |  |  |  |  | B = Approved as Noted/Comments as Noted.
Transmittal. No.: |  | MRC.HH.01-ARN-APM-MAR-0001 |  |  |  |  | C = Revise and Resubmit for approval.
OCS Date: |  | 2018-12-12 |  |  |  |  | D = For Information/Voided. |  |  | `
The document(s) reviewed under this OCS, were issued "For Review and Comments" and are hereby return to the issuer with the following return code and actions request:
Overall Assessment Code: |  | Please write the overall assessment code
S/N | Document Title | Rev. No. | Document Ref. No. | Discipline Engineer | Assessment Code | HFD / Consultant Comments |  | Consultant/Contractor Response | Status
1 | TestTitle |  | TestRef |  |  | Schedule of works to include upcoming milestones. |  |  | Open
[6 empty] | Schedules of works to include milestones . Please include all major milestones. |  | Confirm approx number of milestones required.
[6 empty] | HFD / Consultant Response |  | Consultant/Contractor Response
[6 empty] | [Insert any further Comments here] |  | [Insert any further Respone here]
2 | Monthly Progress Report December 2018 | 00 | MRC.HH.01-ARN-APM-MR-004-00 | Elsayed Mohamed (ARN) | C | Schedule of works to include upcoming milestones. |  | Confirm approx number of milestones required. | Open
Schedule of works to include upcoming milestones. Please include all major milestones.
[6 empty] | HMC-HFD / PMC Response |  | Consultant/Contractor Response
[6 empty] | Include all major milestones. Include at least 1 per week. |  | Report wil be resubmitted with major milestones.

## status
Closed
Open
Pending